## Slide 1
Cap Collective Launch Week
Run-of-Show & Communications Kit — 5 Days to Live Program

## Slide 2
Launch Week Overview
• Goal: From zero to live collection + first caps processed in 5 days
• Audience: Entire school community (students, staff, parents, partners)
• Theme: "Join the Bridge — Create the Impact"
• Daily rhythm: Morning announcement → Activity → Reflection → Data entry
• Culmination: Friday "First Batch Celebration" with product reveal
Cap Collective Launch Week — capcollective.org

## Slide 3
Monday — Kickoff & Box Building
• 🌅 7:30 AM: Green Team sets up boxes in 5 zones (café, gym, entry, library, hallway)
• 📢 8:00 AM: All-school announcement (script in kit) + Launch Deck mini-assembly (15 min)
• 🔨 9:00 AM: "Box Building Day" — K-5 decorate, 6-12 assemble laser-cut kits
• 📦 11:00 AM: Boxes deployed, IR sensors tested, dashboard goes live
• 📝 1:00 PM: First collection log entries, student role applications open
• 📱 3:00 PM: Social media launch — #CapCollectiveLaunch #FeedTheBox
• 📧 4:00 PM: Parent email #1 sent (template in kit)
Cap Collective Launch Week — capcollective.org

## Slide 4
Tuesday — Safety Certification & First Collection
• 🌅 7:30 AM: Box check — swap full boxes, log counts
• 🛡️ 8:30 AM: Safety Certification Stations (rotate every 20 min):
• Station A: Heat Press (temp check, parchment sandwich, timing)
• Station B: Shredder (feed rate, plunger use, sieve test)
• Station C: Wash/Dry (liner removal, soap, 24hr dry)
• Station D: QC (caliper check, batch logging, sign-off)
• ✅ 11:30 AM: Certified students get role badges + lanyards
• 🗑️ 1:00 PM: First official Friday-style collection run
• 📊 2:30 PM: Data Analysts enter counts → dashboard updates live
• 📧 4:00 PM: Parent email #2 — "Ask your student about their role!"
Cap Collective Launch Week — capcollective.org

## Slide 5
Wednesday — Process Cycle Begins
• 🌅 7:30 AM: Collection + weigh-in
• 🧼 8:00 AM: Wash Station — all caps from Mon/Tue washed, drying racks loaded
• ⚙️ 10:00 AM: Shredder Demo — certified operators run first batch, sieve to 5-8mm
• 🔥 11:30 AM: Heat Press Demo — flakes → sheet (140°C HDPE, 5+5+5 min)
• ❄️ 1:00 PM: Cool under weight, QC check, first sheet photographed
• 📊 2:00 PM: Data entry — weight, yield %, flake quality notes
• 🎨 2:30 PM: Design Engineers start Tinkercad coaster designs (K-5: decorate templates)
• 📧 4:00 PM: Staff update email — "Week 1 progress: X caps, Y kg, Z students certified"
Cap Collective Launch Week — capcollective.org

## Slide 6
Thursday — Product Development Sprint
• 🌅 7:30 AM: Collection + weigh-in
• ✂️ 8:00 AM: Laser Cut Demo — coaster frame cuts 4 coasters from sheet
• 🎨 9:30 AM: Design Sprint — students iterate coaster designs, vote on top 3
• 📦 11:00 AM: First coaster batch pressed, cut, sanded, branded
• 💰 1:00 PM: Business Managers calculate COGS, set pilot price ($8-12/set)
• 📸 2:00 PM: Product photography for store/website
• 📊 2:30 PM: Dashboard check — update collection trends, product inventory tab
• 📱 3:00 PM: Student takeover — Instagram/TikTok "Day in the Life"
• 📧 4:00 PM: Community partner email — "Come see our launch Friday!"
Cap Collective Launch Week — capcollective.org

## Slide 7
Friday — Launch Celebration & First Sale
• 🌅 7:30 AM: Final collection of the week — weigh, log, celebrate totals
• 🎉 9:00 AM: "First Batch Celebration" Assembly (30 min):
• • Student leads present: caps collected, kg diverted, CO2e saved
• • Reveal first coaster sets — student designers recognized
• • Principal & partners speak
• • Live dashboard on screen — real-time counter
• 🏪 10:30 AM: POP-UP ECO-STORE OPENS — first sales to students/staff
• 📊 12:00 PM: Sales data entered → P&L calculated live
• 📝 1:00 PM: Reflection circles — "What surprised you? What's next?"
• 📱 2:00 PM: Press release sent (template in kit) + social media blitz
• 📧 4:00 PM: Weekly Impact Report #1 emailed to all stakeholders
Cap Collective Launch Week — capcollective.org

## Slide 8
Communications Templates Included
Template | Audience | Timing | Channel
All-School Announcement Script | Students/Staff | Mon 8:00 AM | PA System / Video
Parent Email #1: "We're Launching!" | Parents | Mon 4:00 PM | Email / Newsletter
Parent Email #2: "Ask About Their Role" | Parents | Tue 4:00 PM | Email
Staff Weekly Update | Teachers/Admin | Daily 4:00 PM | Email / Slack
Community Partner Invitation | Local Cafés/Businesses | Thu 4:00 PM | Email / Print
Press Release | Local Media | Fri 2:00 PM | Email / Wire
Social Media Pack (7 posts) | Community | Mon-Fri | Instagram/FB/Twitter
Student Takeover Guide | Students | Fri | Instagram Stories
Impact Report #1 | All Stakeholders | Fri 4:00 PM | Email / PDF
Grant Progress Update | Funders | Fri 4:00 PM | Email / Portal
Cap Collective Launch Week — capcollective.org

## Slide 9
Social Media Content Calendar
Day | Post Theme | Visual | Hashtags | Student Lead
Monday | Launch Announcement | Box building photos | #CapCollectiveLaunch #FeedTheBox | Comm Lead
Tuesday | Safety First | Certification badges | #SafetyFirst #StudentLed | Safety Lead
Wednesday | Process Reveal | Shredder/press video | #CircularEconomy #Upcycle | Tech Lead
Thursday | Design Sprint | Coaster designs | #StudentDesign #STEAM | Design Lead
Friday | CELEBRATION! | First products + sales | #LaunchDay #ZeroWaste | All Leads
Weekend | Impact Summary | Dashboard screenshot | #WeeklyImpact #DataDriven | Data Lead
Next Mon | Week 2 Preview | Next week goals | #Week2 #Momentum | Program Lead
Cap Collective Launch Week — capcollective.org

## Slide 10
Launch Week Success Metrics
• ✅ 5+ collection boxes deployed and logging data
• ✅ 20+ students safety certified across 4+ stations
• ✅ 500+ caps collected, weighed, and logged
• ✅ 1+ full process cycle completed (collect → clean → shred → press → refine)
• ✅ 1+ product batch finished (coasters/keychains) and QC passed
• ✅ $100+ in first-day sales at pop-up store
• ✅ Dashboard live with real data, shared publicly
• ✅ 3+ parent/community communications sent
• ✅ 1+ press/social media mention
• ✅ All stakeholders received Friday Impact Report
Cap Collective Launch Week — capcollective.org

## Slide 11
Risk Mitigation — "What If?" Scenarios
Risk | Likelihood | Impact | Mitigation (in kit)
Low collection Day 1 | Medium | Low | Backup caps from cafeteria; announce challenge
Equipment delay | Medium | High | Core tier uses hand tools; press later
Safety incident | Low | Critical | SOPs, certifications, 1:4 ratio, stop-work authority
Sensor failure | Medium | Low | Manual entry fallback; CSV import to Sheets
Low student sign-up | Low | Medium | Role cards + gamification (24_ENGAGEMENT_GUIDE)
Admin pushback | Low | High | 12_SCHOOL_BUYIN_PLAYBOOK + admin checklist
Weather (outdoor boxes) | Medium | Low | Indoor backup zones identified
Cap Collective Launch Week — capcollective.org

## Slide 12
Thank You — Let's Launch!
Every cap counts. Every student leads. Every week grows.